## Amdocs
Total Amdocs cases owned by Symon Storozhenko as QA resource
Case # | Title | SQA Status | Severity | Amdocs case status | Triaged by QA | Reproduced | Left a note | Internal note | Reassigned further | Jira opened | Tested after fix | Passed after fix | Comments
160421-48558 | VHI; Big Lots; Vantiv Response Code 110 not covered by VHI properly | Waiting for Fix | S2 Major | IT- Investigating | yes | yes | yes | yes | no | PTMX-1361 PTMX-1362 |  |  | Will be resolved with VHI 1.00.10. Amdocs and Jiras updated
160427-14675 | MX915, EMV Void Issue - Converts to Decline and Customer charged | Fixed | S1 Critical | New Case | yes | no | yes | yes | yes. Winfield | PTMX-1352 |  |  | Fixed with VHI 1.00.06 B5. Amdocs and Jiras updated
160427-14694 | No response returned from SCA when invalid line item request is sent from POS | Fixed | S2 Major | IT- Investigating | yes | yes | yes | yes | yes | PTMX-1367 closed | yes | yes | Fixed with 2.19.25 B2
160201-2849 | SECONDARYPORT CANCEL not always sending both responses | Fixed | S2 Major | IT- In SQA | no | no | yes | yes | yes | n/a | yes | yes | Fixed
160511-14433 | SCA; Carters; Terminal Capability values are inconsistent | Pending info from SE/Customer | S2 Major | New Case |  |  | yes | yes | yes |  |  |  | Asked for more info and logs.
160422-54108 | MX915, FIVE BELOW - Media Package failure on XPI screens | Pending info from SE/Customer | S1 Critical | New Case | yes | no | yes | yes | yes | no |  |  | Couldn't recreate
160325-22038 | Device freezing | Fixed | S1 Critical | Investigating | yes | no | yes | yes | yes | no | yes | yes | Fixed
160523-2604 | MX925 ;Token Query Response Invalid Expiration Date | Waiting for Fix | S2 Major | New Case | yes | yes | yes | no | no | PTMX-1429 |  |  | Waiting for Fix
Pending AMDOCS
Amdocs Case # | Title |  | Amdocs Severity | Status | Jira opened | Jira Severity

## Jiras
Total Jira tickets owned by Symon Storozhenko as QA resource
Ticket # | Title | Severity | Status | Reproducible | Tested after fix | Passed after fix | Comments
PTMX-1388 | SCA returning wrong 9F02 tag value with partial capture | Critical | Closed | yes | yes | yes | Defect is fixed with 2.19.25 B5
PTMX-1361 | AMDOCS 160421-48558: VHI TOR response is not parsed by SCA | High | Unresolved | yes |  |  | Will be resolved with VHI 1.00.10
PTMX-1362 | AMDOCS 160421-48558: VHI TOR response timed out. | High | Unresolved | yes |  |  | Will be resolved with VHI 1.00.10
PTMX-1352 | Amdocs #160427-14675; VHI - Void is not approving by host | Critical | Closed | yes |  |  | Fixed with VHI 1.00.06 B5
PTMX-1367 | AMDOCS 160427-14694: No response returned from SCA when invalid line item request is sent from POS | High | Closed | yes | yes | yes | Fixed with 2.19.25 B2
PTMX-1390 | SCA is sending wrong <PAYMENT_TYPE> in void request to ADS Gateway | Meduim | Closed | yes | yes | yes | Fixed with 2.19.25 B3
PTMX-1407 | 2.19.23 B9 - SCA is asking for cashback when <PAYMENT_TYPE> is CREDIT | Meduim | Closed | yes | N/A | N/A | Closed. SSI guide was updated for <CASHBACK_AMOUNT> to include DEBIT, CREDIT, and EBT
PTMX-1413 | 2.19.23 B9 - Preswipe/preinsert causes device to freeze | Critical | Closed | yes |  |  | Closed. disabled stb_support in [reg] and [iab] sections also

## .25 Jiras
Total Jira tickets owned by Symon Storozhenko as QA resource
Ticket # | Title | Severity | Status | Reproducible | Tested after fix | Passed after fix | Comments | Reported by
PTMX-1342 | SCA doesnt display Tender_Type when POS requests all the tenders using PAYMENT_TYPES field | Medium | Resolved | yes |  |  | resolved
PTMX-1375 | 2.19.24 b3:When SAF query is done for not processed records ,hostrespcode tag has a value of -2 | Low | In Verification | yes |  |  | Please verify with SCA 2.19.25 B1
PTMX-1365 | 2.19.24ADE Build3: Application freezes intermittently in card read screen after i swipe the card after sending an altered BIN file | High | In Verification | yes |  |  | Please verify with SCA 2.19.25 B1
PTMX-707 | McD: 2.19.21 B3 - Contactless EMV and RFID transactions timing issues. | Medium | Unresolved | yes |  |  | Please verify with SCA 2.19.25 B1
PTMX-1403 | SCA 2.19.25 B2 - System allows to frame a request for a debit transaction with transaction amount lesser than the cashback amount. | Medium | Unresolved | yes |  |  |  | Sowmya T.